## No Service Tickets
project_name | beid | project_rid | customer_phone | address | city | state | ahj | submitted_date | install_complete_date | pto_received_date | submitted_to_install_days | install_to_pto_days | status | warehouse | installer | utility | service_ticket_count | escalation_record_count | negative_review_record_count
Hunter Robbins_BE37697 | BE37697 | 13832 | 1 (949) 697-4555 | 1 Lantana, Aliso Viejo, CA 92656 | Aliso Viejo | CA | Aliso Viejo (CA) | 2022-07-26 | 2022-08-20 | 2022-09-20 | 25 | 31 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Juan Bacerra | BE145754 | 45754 | 1 (714) 300-8865 | 9762 Clearbrook Lane, Anaheim, CA 92804 | Anaheim | CA | Orange County (CA) | 2026-03-24 | 2026-04-17 | 2026-05-11 | 24 | 24 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | Southern California Edison | 0 | 0 | 0
Liliane Parra_BE66840 | BE66840 | 20923 | 1 (909) 239-4831 | 1327 S Claremont St, anaheim, CA 92805 | anaheim | CA |  | 2023-08-23 | 2023-10-09 | 2023-11-07 | 47 | 29 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Anaheim Public Utilities | 0 | 0 | 0
Charlanne Merizan | BE135709 | 35709 | 1 (714) 329-0453 | 1250 Ponderosa Avenue, Brea, CA 92821 | Brea | CA | Brea (CA) | 2025-04-18 | 2025-05-17 | 2025-06-18 | 29 | 32 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Terryl Weber II_BE56598 | BE56598 | 32448 | 1 (714) 323-4237 | 5901 Equador Way, Buena Park, CA 90620 | Buena Park | CA | Buena Park (CA) | 2023-03-23 | 2023-04-24 | 2023-06-15 | 32 | 52 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Kyle Young_BE24155 | BE24155 | 20249 | 1 (949) 533-3461 | 1778 Crestmont Pl, Costa Mesa, CA 92627 | Costa Mesa | CA | Costa Mesa (CA) | 2021-10-13 | 2021-11-16 | 2021-12-07 | 34 | 21 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Chase Gilmore_BE4726 | BE4726 | 4417 | 1 (562) 243-2539 | 1740 Missouri St, Costa Mesa, CA 92626 | Costa Mesa | CA | Costa Mesa (CA) | 2021-02-02 | 2021-03-22 | 2021-03-31 | 48 | 9 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Parimal Neupane_BE37570 | BE37570 | 26661 | 1 (617) 756-1643 | 6672 Forest St, Cypress, CA 90630 | Cypress | CA | Cypress (CA) | 2022-07-23 | 2022-08-05 | 2022-10-13 | 13 | 69 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Irma Navejas_BE76642 | BE76642 | 14054 | 1 (714) 335-7697 | 11688 Wake Cir, Cypress, CA 90630 | Cypress | CA | Cypress (CA) | 2024-09-15 | 2024-10-22 | 2024-11-20 | 37 | 29 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Susanne Christensen_BE53332 | BE53332 | 5372 | 1 (480) 703-2264 | 24661 Cordova Dr, Dana Point, CA 92629 | Dana Point | CA | Dana Point (CA) | 2023-03-17 | 2023-05-05 | 2023-06-12 | 49 | 38 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
John Bolling_BE37024 | BE37024 | 16499 | 1 (949) 295-0690 | 33772 Pequito Dr, Dana Point, CA 92629 | Dana Point | CA | Dana Point (CA) | 2022-07-14 | 2022-09-01 | 2022-10-20 | 49 | 49 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Quang Nguyen_BE49371 | BE49371 | 27608 | 1 (714) 653-8313 | 8598 Woodpecker Ave, Fountain Valley, CA 92708 | Fountain Valley | CA | Fountain Valley (CA) | 2023-02-10 | 2023-03-08 | 2023-04-12 | 26 | 35 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jason Schanta_BE4728 | BE4728 | 15094 | 1 (760) 458-6488 | 18801 Deodar St, Fountain Valley, CA 92708 | Fountain Valley | CA | Fountain Valley (CA) | 2021-01-28 | 2021-03-18 | 2021-04-06 | 49 | 19 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Shannon Heard_BE53460 | BE53460 | 31501 | 1 (562) 225-0840 | 1218 W Ash Ave, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2023-03-15 | 2023-04-03 | 2023-05-18 | 19 | 45 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Raquel Straske | BE146313 | 46313 | 1 (714) 876-5251 | 1105 West Oak Avenue, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2026-04-17 | 2026-05-15 | 2026-06-24 | 28 | 40 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | Southern California Edison | 0 | 0 | 0
Julio Garcia_BE28636 | BE28636 | 18950 | 1 (323) 453-0661 | 205 N Florence Pl, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2022-02-20 | 2022-03-22 | 2022-04-08 | 30 | 17 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Luis Rodriguez_BE46634 | BE46634 | 21666 | 1 (347) 512-7483 | 200 S Muroc Pl, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2023-01-10 | 2023-02-10 | 2023-04-03 | 31 | 52 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Theodore Laase_BE57755 | BE57755 | 32552 | 1 (714) 526-4454 | 2110 Domingo Rd, Fullerton, CA 92835 | Fullerton | CA | Fullerton (CA) | 2023-03-29 | 2023-05-02 | 2023-07-21 | 34 | 80 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Vivienne Wang_BE76135 | BE76135 | 34087 | 1 (626) 898-1128 | 3019 Limewood Ct, Fullerton, CA 92835 | Fullerton | CA |  | 2024-08-28 | 2024-10-03 | 2024-12-18 | 36 | 76 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Richard Jolliffe_BE51792 | BE51792 | 28823 | 1 (714) 855-8426 | 1500 S Orchard Ave, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2023-03-05 | 2023-04-21 | 2023-06-28 | 47 | 68 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Andrew Said_BE52794 | BE52794 | 1999 | 1 (562) 291-9124 | 1504 Welldow Ln, Fullerton, CA 92831 | Fullerton | CA | Fullerton (CA) | 2023-03-15 | 2023-05-04 | 2023-07-12 | 50 | 69 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Susan Lee_BE50456 | BE50456 | 5431 | 1 (714) 980-1686 | 1300 W Valencia mesa Dr, Fullerton, CA 92833 | Fullerton | CA | Fullerton (CA) | 2023-02-27 | 2023-04-24 | 2023-06-28 | 56 | 65 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Camille Munganga_BE56341 | BE56341a | 3792 | 1 (714) 458-0207 | 13451 Barnett Way, Garden Grove, CA 92843 | Garden Grove | CA | Garden Grove (CA) | 2023-03-24 | 2023-04-21 | 2023-06-29 | 28 | 69 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Lee Anderson_BE30101 | BE30101 | 20597 | 1 (310) 505-4004 | 20391 Mooncrest Cir, Huntington Beach, CA 92646 | Huntington Beach | CA | Huntington Beach (CA) | 2022-03-10 | 2022-04-01 | 2022-05-18 | 22 | 47 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Gerald Kehler_BE21186 | BE21186 | 12345 | 1 (714) 713-5897 | 8171 Malloy Dr, Huntington Beach, CA 92646 | Huntington Beach | CA | Huntington Beach (CA) | 2021-06-22 | 2021-07-14 | 2021-09-03 | 22 | 51 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Marcee Booth_BE21336 | BE21336 | 22149 | 1 (714) 767-3072 | 6571 Jardines Dr, Huntington Beach, CA 92647 | Huntington Beach | CA | Huntington Beach (CA) | 2021-07-02 | 2021-07-28 | 2021-09-14 | 26 | 48 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jim Otto_BE25911 | BE25911 | 16130 | 1 (714) 722-7537 | 15552 Wild Plum Cir, Huntington Beach, CA 92647 | Huntington Beach | CA | Huntington Beach (CA) | 2021-11-10 | 2021-12-08 | 2022-01-12 | 28 | 35 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Ron Hughes_BE28438 | BE28438 | 15566 | 1 (949) 233-7432 | 15402 La Salle Ln, Huntington Beach, CA 92647 | Huntington Beach | CA | Huntington Beach (CA) | 2022-02-13 | 2022-03-14 | 2022-05-20 | 29 | 67 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Prakash Divecha_BE23454 | BE23454 | 27485 | 1 (805) 990-5330 | 26 Carver, Irvine, CA 92620 | Irvine | CA |  | 2021-09-29 | 2021-10-21 | 2021-11-18 | 22 | 28 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Edmon Girgis_BE42902 | BE42902 | 9806 | 1 (661) 380-0477 | 161 Church Pl, Irvine, CA 92602 | Irvine | CA | Irvine (CA) | 2022-10-20 | 2022-11-14 | 2023-01-13 | 25 | 60 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
David Haney_BE56411 | BE56411 | 8398 | 1 (949) 981-6962 | 19 Newmeadow, Irvine, CA 92614 | Irvine | CA | Irvine (CA) | 2023-03-22 | 2023-04-19 | 2023-06-13 | 28 | 55 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Yue Li | BE3563 | 34939 | 1 (919) 600-0935 | 4 Wharton Ct, Irvine, CA 92617 | Irvine | CA | Irvine (CA) | 2020-12-10 | 2021-01-21 | 2021-02-11 | 42 | 21 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Shayan Minaie_BE1827 | BE1827 | 31645 | 1 (949) 500-3736 | 67 Furlong, Irvine, CA 92602 | Irvine | CA |  | 2020-06-04 | 2020-07-31 | 2020-09-10 | 57 | 41 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jacob Shubin_BE48653 | BE48653 | 14361 | 1 (562) 371-4167 | 1060 Edgemont St, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2023-02-02 | 2023-02-17 | 2023-03-27 | 15 | 38 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Nancy Adams_BE55486 | BE55486 | 25509 | 1 (562) 260-7092 | 641 Laura St, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2023-03-16 | 2023-04-05 | 2023-05-24 | 20 | 49 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Camilo Ruiz_BE51080 | BE51080 | 3795 | 1 (562) 716-2132 | 741 Sturbridge Dr, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2023-03-02 | 2023-03-30 | 2023-06-27 | 28 | 89 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jared Higgins_BE53399 | BE53399 | 14961 | 1 (707) 483-7946 | 2621 Candlewood Way, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2023-03-15 | 2023-04-14 | 2023-06-16 | 30 | 63 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Craig Deutsch_BE55771 | BE55771 | 5068 | 1 (619) 787-8995 | 1420 Arbolita Dr, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2023-03-21 | 2023-05-05 | 2023-06-28 | 45 | 54 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Pablo Cerda_BE43576 | BE43576 | 26562 | 1 (714) 353-1472 | 2250 Canterbury Ln, La Habra, CA 90631 | La Habra | CA | La Habra (CA) | 2022-11-04 | 2022-12-22 | 2023-03-08 | 48 | 76 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Pacific Gas & Electric | 0 | 0 | 0
Ruben Eliana_BE35614 | BE35614 | 30143 | 1 (562) 537-5202 | 5841 Calaveras Cir, La Palma, CA 90623 | La Palma | CA | La Palma (CA) | 2022-06-23 | 2022-07-25 | 2022-10-08 | 32 | 75 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Raphael Illouz | BE138118 | 38118 | 1 (949) 466-3787 | 42 Bainbridge Avenue, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2025-10-08 | 2025-10-24 | 2025-12-23 | 16 | 60 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Kelvin Mcclaskey_BE80535 | BE80535 | 19645 | 1 (714) 715-3628 | 30 Falkner Dr, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2025-03-11 | 2025-03-28 | 2025-04-22 | 17 | 25 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Patricia Fukushima_BE56039 | BE56039 | 26738 | 1 (949) 689-9285 | 5 Risa St, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2023-03-20 | 2023-04-07 | 2023-06-19 | 18 | 73 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Eric Popkowski_BE76224 | BE76224 | 10611 | 1 (949) 726-2076 | 22 University Ave, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2024-08-30 | 2024-09-24 | 2024-10-07 | 25 | 13 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Simon Flax | BE135733 | 35733 | 1 (646) 207-0554 | 7 Crestmont Court, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2025-04-19 | 2025-05-20 | 2025-08-14 | 31 | 86 | COMPLETED | Cerritos, CA | Earthbound Solar DBA Earthbound Electric;QB16331 | San Diego Gas & Electric | 0 | 0 | 0
Mrugesh Patel | BE138413 | 38413 | 1 (630) 965-8889 | 2 Entonar Road, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2025-11-11 | 2025-12-20 | 2026-02-10 | 39 | 52 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | San Diego Gas & Electric | 0 | 0 | 0
Lorenz Siongco_BE3804 | BE3804 | 21269 | 1 (818) 648-1576 | 35 Vivido St, Ladera Ranch, CA 92694 | Ladera Ranch | CA | Orange County (CA) | 2020-10-16 | 2020-12-14 | 2021-02-22 | 59 | 70 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Khosrow Mirhadi_BE21029 | BE21029 | 19934 | 1 (949) 244-1355 | 24816 Solano Ct, Laguna Hills, CA 92653 | Laguna Hills | CA | Laguna Hills (CA) | 2021-06-11 | 2021-06-30 | 2021-08-20 | 19 | 51 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Jose Bautista | BE1237 | 17354 | 1 (949) 421-8242 | 24941 Largo Dr, Laguna Hills, CA 92653 | Laguna Hills | CA | Laguna Hills (CA) | 2020-09-18 | 2020-10-28 | 2020-12-10 | 40 | 43 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Joe Philbin | BE146062 | 46062 | 1 (714) 904-9860 | 10 Capri, Laguna Niguel, CA 92677 | Laguna Niguel | CA | Laguna Niguel (CA) | 2026-04-07 | 2026-05-01 | 2026-07-02 | 24 | 62 | IN PROGRESS | Cerritos, CA | Better Earth;QB21550 | San Diego Gas & Electric | 0 | 0 | 0
David Gaylord_BE42254 | BE42254 | 8382 | 1 (949) 939-6011 | 27842 Homestead Rd, Laguna Niguel, CA 92677 | Laguna Niguel | CA | Laguna Niguel (CA) | 2022-10-06 | 2022-11-16 | 2023-02-06 | 41 | 82 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Chris Martin_BE21263 | BE21263 | 4553 | 1 (949) 307-4967 | 24961 Owens Lake Cir, Lake Forest, CA 92630 | Lake Forest | CA | Lake Forest (CA) | 2021-07-01 | 2021-07-15 | 2021-08-03 | 14 | 19 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Brooke Millard_BE28476 | BE28476 | 3673 | 1 (949) 616-2827 | 24766 Camino Villa, Lake Forest, CA 92630 | Lake Forest | CA | Lake Forest (CA) | 2022-02-22 | 2022-03-22 | 2022-05-11 | 28 | 50 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Eilif Trondsen_BE5733 | BE5733 | 10025 | 1 (408) 386-4304 | 11922 Weatherby Rd, Los Alamitos, CA 90720 | Los Alamitos | CA | Orange County (CA) | 2021-04-09 | 2021-04-30 | 2021-06-17 | 21 | 48 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
David Sorem_BE45920 | BE45920 | 8601 | 1 (562) 881-9553 | 3182 Quail Run Rd, Los Alamitos, CA 90720 | Los Alamitos | CA | Orange County (CA) | 2022-12-28 | 2023-01-19 | 2023-04-12 | 22 | 83 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jessy Benavente _BE51194 | BE51194 | 15856 | 1 (949) 370-5063 | 15 Pemberly, Mission Viejo, CA 92692 | Mission Viejo | CA | Mission Viejo (CA) | 2023-03-01 | 2023-03-24 | 2023-05-18 | 23 | 55 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Sahar Moshksaran_BE21455 | BE21455 | 30474 | 1 (310) 920-1253 | 25062 Whitespring, Mission Viejo, CA 92692 | Mission Viejo | CA | Mission Viejo (CA) | 2021-07-13 | 2021-08-12 | 2021-11-01 | 30 | 81 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Tony Acevedo_BE51591 | BE51591 | 33105 | 1 (949) 306-1041 | 29 Chesterfield, Mission Viejo, CA 92692 | Mission Viejo | CA | Mission Viejo (CA) | 2023-03-03 | 2023-04-05 | 2023-05-25 | 33 | 50 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Alma G DeGarcia_BE21549 | BE21549 | 1568 | 1 (714) 510-6382 | 24861 Clavel, Mission Viejo, CA 92692 | Mission Viejo | CA | Mission Viejo (CA) | 2021-07-27 | 2021-09-02 | 2021-09-22 | 37 | 20 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Nick Punto | BE138583 | 38583 | 1 (949) 632-8511 | 25 Friar Lane, Mission Viejo, CA 92694 | Mission Viejo | CA | Orange County (CA) | 2025-12-04 | 2026-01-10 | 2026-03-19 | 37 | 68 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | San Diego Gas & Electric | 0 | 0 | 0
Scott Nichols | BE1880 | 31193 | 1 (949) 229-9293 | 23611 Rangoon St, Mission Viejo, CA 92691 | Mission Viejo | CA |  | 2020-05-21 | 2020-07-06 | 2020-07-24 | 46 | 18 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Barbra Seay_BE52241 | BE52241 | 2996 | 1 (949) 378-5838 | 27 Hollyhock Ln, Mission Viejo, CA 92692 | Mission Viejo | CA | Mission Viejo (CA) | 2023-03-13 | 2023-05-03 | 2023-07-12 | 51 | 70 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Eliisa Stowell_BE20858 | BE20858 | 10130 | 1 (949) 903-0026 | 527 Seaward Rd, Newport Beach, CA 92625 | Newport Beach | CA | Newport Beach (CA) | 2021-05-28 | 2021-06-16 | 2021-07-16 | 19 | 30 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Maria Navis_BE30399 | BE30399 | 22731 | 1 (714) 813-7125 | 294 W Pebble Creek Ln, Orange, CA 92865 | Orange | CA | Orange (CA) | 2022-03-17 | 2022-03-31 | 2022-06-03 | 14 | 64 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Javier Sandoval_BE47215 | BE47215 | 15197 | 1 (949) 705-9829 | 246 N Bitterbush St, Orange, CA 92868 | Orange | CA | Orange (CA) | 2023-01-17 | 2023-02-01 | 2023-03-14 | 15 | 41 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Ryan Hanstad_BE57052 | BE57052 | 30360 | 1 (714) 390-9797 | 1045 N Mallard St, Orange, CA 92867 | Orange | CA | Orange (CA) | 2023-03-26 | 2023-04-18 | 2023-06-28 | 23 | 71 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Liliane Parra | BE138443 | 38443 | 1 (909) 269-4813 | 1147 East Chestnut Avenue, Orange, CA 92867 | Orange | CA | Orange (CA) | 2025-11-14 | 2025-12-11 | 2026-01-19 | 27 | 39 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | Southern California Edison | 0 | 0 | 0
Ty Thomas_BE27895 | BE27895 | 33328 | 1 (714) 767-3159 | 531 E Trenton Ave, Orange, CA 92867 | Orange | CA | Orange (CA) | 2022-01-25 | 2022-03-01 | 2022-04-18 | 35 | 48 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
liliane parra_BE66842 | BE66842 | 20925 | 1 (909) 269-4813 | 1147 E Chestnut Ave, orange, CA 92867 | orange | CA |  | 2023-08-23 | 2023-10-02 | 2023-12-12 | 40 | 71 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Valentin Sezonov_BE30780 | BE30780 | 33433 | 1 (714) 244-6596 | 1521 E Ray Dr, Placentia, CA 92870 | Placentia | CA | Placentia (CA) | 2022-03-25 | 2022-04-05 | 2022-06-01 | 11 | 57 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Steven Myers_BE29037 | BE29037 | 5606 | 1 (714) 984-4924 | 716 Sue Dr, Placentia, CA 92870 | Placentia | CA | Placentia (CA) | 2022-03-07 | 2022-04-29 | 2022-06-03 | 53 | 35 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Tim Sullivan | BE1996 | 32828 | 1 (714) 458-8228 | 5 Cerro Court, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-04-14 | 2020-04-28 | 2020-07-13 | 14 | 76 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Kyle Flanagan_BE1989 | BE1989 | 20214 | 1 (949) 838-5541 | 14 Alza St, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-04-16 | 2020-05-19 | 2020-07-14 | 33 | 56 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Tania Perry_BE2007 | BE2007 | 32192 | 1 (949) 246-4842 | 135 Garcilla Drive, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-04-10 | 2020-05-13 | 2020-07-20 | 33 | 68 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Gary Warren_BE2022 | BE2022 | 12151 | 1 (949) 370-1030 | 111 Garcilla Drive, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-04-01 | 2020-05-11 | 2020-07-16 | 40 | 66 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Anthony Greenberg_BE4538 | BE4538 | 2292 | 1 (949) 735-0511 | 209 Garcilla Drive, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-03-11 | 2020-04-21 | 2020-05-18 | 41 | 27 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Vicki Thompson_BE1820 | BE1820 | 33673 | 1 (949) 239-2638 | 187 Garcilla Dr, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-06-06 | 2020-07-23 | 2020-08-31 | 47 | 39 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Gloria Lifschutz_BE4539 | BE4539 | 29060 | 1 (949) 940-5964 | 147 Garcilla Dr, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-03-13 | 2020-05-04 | 2020-05-15 | 52 | 11 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Phillip Trent_BE1864 | BE1864 | 27389 | 1 (949) 652-1625 | 127 Garcilla Drive, Rancho Mission Viejo, CA 92694 | Rancho Mission Viejo | CA |  | 2020-05-28 | 2020-07-21 | 2020-09-23 | 54 | 64 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Joseph Benton_BE21009 | BE21009 | 18097 | 1 (949) 702-4666 | 34 Acorn Ridge, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Orange County (CA) | 2021-06-10 | 2021-06-29 | 2021-08-11 | 19 | 43 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Teresita Hidalgo_BE21041 | BE21041 | 32362 | 1 (949) 705-7138 | 19 Silkwood Ln, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Orange County (CA) | 2021-06-04 | 2021-06-24 | 2021-08-09 | 20 | 46 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Tim Gavin_BE80244 | BE80244 | 32794 | 1 (714) 713-8386 | 16 Ametrine Way, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Rancho Santa Margarita (CA) | 2025-03-02 | 2025-03-26 | 2025-04-26 | 24 | 31 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Tricia Osborne_BE79047 | BE79047 | 33250 | 1 (949) 433-4171 | 42 Castletree, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Orange County (CA) | 2025-01-13 | 2025-02-11 | 2025-04-14 | 29 | 62 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Steve Vlahos | BE136839 | 36839 | 1 (949) 615-1355 | 11 Shasta Court, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Orange County (CA) | 2025-07-03 | 2025-08-08 | 2025-11-04 | 36 | 88 | COMPLETED | Cerritos, CA | Earthbound Solar DBA Earthbound Electric;QB16331 | San Diego Gas & Electric | 0 | 0 | 0
Jason Kencke_BE79042 | BE79042 | 15006 | 1 (949) 678-8366 | 22 Bergenia, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Rancho Santa Margarita (CA) | 2025-01-12 | 2025-02-24 | 2025-03-15 | 43 | 19 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Akash Kumar_BE48451 | BE48451 | 1089 | 1 (510) 759-8433 | 50 Tradition Ln, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Orange County (CA) | 2023-02-07 | 2023-03-24 | 2023-04-12 | 45 | 19 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Mahendra Rathnayake_BE35304 | BE35304 | 21894 | 1 (949) 532-9922 | 22 Twilight Ln, Rancho Santa Margarita, CA 92688 | Rancho Santa Margarita | CA | Rancho Santa Margarita (CA) | 2022-06-18 | 2022-08-10 | 2022-10-07 | 53 | 58 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
EVAN WEISS | BE138814 | 38814 | 1 (949) 606-4660 | 1715 Calle Alcazar, San Clemente, CA 92672 | San Clemente | CA | San Clemente (CA) | 2026-01-16 | 2026-01-27 | 2026-04-14 | 11 | 77 | COMPLETED | Cerritos, CA | Better Earth;QB21550 | San Diego Gas & Electric | 0 | 0 | 0
Darren Walsh_BE1074 | BE1074a | 8160 | 1 (561) 452-0326 | 419 Via Montego, San Clemente, CA 92672 | San Clemente | CA | San Clemente (CA) | 2021-06-25 | 2021-07-12 | 2021-09-01 | 17 | 51 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Marianne Cole_BE38625 | BE38625 | 22922 | 1 (949) 291-2747 | 2512 Via Durazno, San Clemente, CA 92673 | San Clemente | CA |  | 2022-08-10 | 2022-08-29 | 2022-10-20 | 19 | 52 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
William Pappas_BE41139 | BE41139 | 34498 | 1 (267) 565-0684 | 2508 Via Durazno, San Clemente, CA 92673 | San Clemente | CA | San Clemente (CA) | 2022-09-15 | 2022-10-10 | 2022-11-03 | 25 | 24 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Reni Churchill_BE73833 | BE73833 | 28524 | 1 (949) 275-0914 | 2458 calle aquamarina, San clemente, CA 92673 | San clemente | CA | San Clemente (CA) | 2024-06-17 | 2024-07-22 | 2024-08-06 | 35 | 15 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Kelli Schott | BE136981 | 36981 | 1 (949) 702-7544 | 14 Calle Akelia, San Clemente, CA 92673 | San Clemente | CA | San Clemente (CA) | 2025-07-14 | 2025-08-26 | 2025-09-09 | 43 | 14 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Stephen Gerevas | BE137006 | 37006 | 1 (949) 400-5600 | 2024 Costero Hermoso , San Clemente , CA 92673 | San Clemente | CA | San Clemente (CA) | 2025-07-15 | 2025-08-15 | 2025-09-22 | 31 | 38 | COMPLETED | Cerritos, CA | Better Earth;146899150 | San Diego Gas & Electric | 0 | 0 | 0
Rodney Houser_BE21234 | BE21234 | 29522 | 1 (714) 815-1406 | 1419 N Lowell St, Santa Ana, CA 92706 | Santa Ana | CA | Santa Ana (CA) | 2021-06-24 | 2021-07-14 | 2021-09-16 | 20 | 64 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Hue Le_BE28361 | BE28361 | 13767 | 1 (714) 200-7333 | 3214 Park Dr, Santa Ana, CA 92707 | Santa Ana | CA | Santa Ana (CA) | 2022-02-10 | 2022-03-08 | 2022-03-16 | 26 | 8 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Lola Isenhour_BE3509 | BE3509 | 21209 | 1 (714) 277-9798 | 12712 Bubbling Well Rd, Santa Ana, CA 92705 | Santa Ana | CA | Orange County (CA) | 2020-12-08 | 2021-01-07 | 2021-02-10 | 30 | 34 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Alma Unsworth_BE21859 | BE21859 | 1583 | 1 (714) 722-0803 | 519 Jenkins St, Santa Ana, CA 92703 | Santa Ana | CA | Santa Ana (CA) | 2021-08-11 | 2021-09-15 | 2021-10-11 | 35 | 26 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Cristina Yanez_BE33543 | BE33543 | 5128 | 1 (949) 355-6330 | 618 W Alpine Ave, Santa Ana, CA 92707 | Santa Ana | CA | Santa Ana (CA) | 2022-05-25 | 2022-07-01 | 2022-08-18 | 37 | 48 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Sagel Simon_BE51168 | BE51168 | 30476 | 1 (714) 420-0026 | 1227 E 14th St, Santa Ana, CA 92701 | Santa Ana | CA | Santa Ana (CA) | 2023-03-01 | 2023-04-07 | 2023-06-28 | 37 | 82 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Christina Flores_BE78276 | BE78276 | 7374 | 1 (714) 222-0942 | 2609 W Harvard Street, Santa Ana, CA 92704 | Santa Ana | CA | Santa Ana (CA) | 2024-11-19 | 2024-12-30 | 2025-01-22 | 41 | 23 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Diana Salgado_BE33031 | BE33031 | 9122 | 1 (714) 335-3169 | 415 E Camile St, Santa Ana, CA 92701 | Santa Ana | CA | Santa Ana (CA) | 2022-05-11 | 2022-06-24 | 2022-08-15 | 44 | 52 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Jose Arturo Mendez Herrera_BE45791 | BE45791 | 17328 | 1 (714) 856-5872 | 509 S Pacific Ave, Santa Ana, CA 92703 | Santa Ana | CA | Santa Ana (CA) | 2022-12-23 | 2023-02-08 | 2023-03-22 | 47 | 42 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Sava Knezevich_BE1153 | BE1153 | 31106 | 1 (714) 330-4022 | 16292 Lunar St, Westminster, CA 92683 | Westminster | CA | Westminster (CA) | 2020-09-24 | 2020-10-21 | 2020-12-01 | 27 | 41 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Masashi Miyaoka_BE25789 | BE25789 | 23778 | 1 (714) 892-3717 | 5281 Tattershall Ave, Westminster, CA 92683 | Westminster | CA | Westminster (CA) | 2021-11-09 | 2021-12-09 | 2022-01-13 | 30 | 35 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0
Selena Williams_BE21266 | BE21266 | 31305 | 1 (714) 862-5251 | 8811 St Andrews Ave, Westminster, CA 92683 | Westminster | CA | Westminster (CA) | 2021-06-26 | 2021-08-09 | 2021-10-11 | 44 | 63 | COMPLETED | Cerritos, CA | Better Earth;146899150 | Southern California Edison | 0 | 0 | 0